## Version History
Process Improvement Action Plan v 1.2
Project: OMMCOM News
Sl. No. | Version No | Date | Prepared by | Reviewed by | Reviewed On | Approved by | Approved on | Change Details
1 | 1 | 2016-02-09 | Satyakam Misra | Tanmay Mohanty | 2016-02-09 | Tanmay Mohanty | 2016-02-09 | Process Improvement Input form required added
2 | 1.1 | 2016-04-01 | Satyakam Misra | Debasish Mishra | 2016-04-01 | Debasish Mishra | 2016-04-01 | Usage of work update tools added
3 | 1.2 | 2016-04-25 | Satyakam Misra | Debasish Mishra | 2016-04-25 | Debasish Mishra | 2016-04-25 | IM communication added
Classification:Luminous Infoways Pvt. Ltd. ¦ CONFIDENTIAL

## Process Improvement Action Plan
Process Improvement Action Plan
Sl. No | Improvement Area | Improvement opportunity | Date Identified | Trigger | Type | Action | Impacted Items |  |  |  | Remarks | Responsibility | Target Date for Closure | Status
Sl. No | [6 empty] | Process | Guidelines | Templates | Checklists
1 | Request for process improvement | Forms needed where human resources shall be able to provide their input regarding the improvement in processes we follow | 2016-02-09 | Process Improvement Input form not available | New | Add Process Improvement Input form | - | - | - | - | Process Improvement Input form included which has made it easier for human resources to provide their inputs regarding the improvement in existing processes | Satyakam | 2016-02-10 | Implemented
2 | Work Update | Usage of tools to make the work updation on a daily basis easier | 2016-04-01 | It is difficult to track daily work updates in detail | New | Analysis of all such tools has to be done and the best suited tool to be identified and acquired | - | - | - | - | PMIS tool has been implemented in which an individual is able to update work against task assigned on a daily basis | Mausumi | 2016-04-04 | Implemented
3 | Communication | IM shall be used for immediate project related communications in project groups created | 2016-04-25 | One to one discussion led to communication gap between the entire team. All were not on the same page. | New | IM shall be used for project related discussion. All the project assignees shall communicate in the project group created. | - | - | - | - | Currently IM is used within team which has made it easier for everyone to be on the same page. | Satyakam | 2016-04-25 | Implemented
Note on G5: - Incremental (Needs Modification) - New - To be Practiced
Note on I5: Use Change Request Tracker for making changes to the existing QMS documents