## MoM
Minutes of Meeting
Project Name /Function Name |  | OMMCOM NEWS |  | Date | 2016-04-16
Meeting Called By |  | Tanmay Mohanty |  | Topic | Review of Progess of Development
Schedule Time of Start |  | Actual Time of Start |  | Venue
05.00 PM |  | 05.00 PM |  | Luminous Infoways Pvt. Ltd, BBSR
Planned Duration of the Meeting |  | Actual Duration of the Meeting |  | Date/ Time/ Venue of Next Meeting
1 Hours |  | 1:00 Hrs |  | 30-Apr-2016/5:00 PM/Luminous Infoways Pvt. Ltd.
Members Present |  | Satyakam Misra (System Analyst), Debasish Mishra (PM), Mr. Tanmay Mohanty(CEO), Sarada Prasana Behera(DGM Op.), Mausumi Panda(QA), Samadhan Mishra(Technical Architect)
Members Absent |  | Not Available
Invitees |  | Not Available
Objectives of the Meeting |  | Discussion on Progress of the OMMCOM Application
Pending Action Points from Previous Meeting
S.No. | Action/ Observation | Responsibility | Projected Date of completion | Closure status/ Date of closure | Remarks
1 | SRS need to be Complete in all aspect | Satyakam | 2016-04-13 | Closed/ 13-Apr-16
2 | Technical Solution of the Application need to be freezed | Samadhan | 2016-04-15 | Closed/15-Apr-16
3 | UI needs to be approved from the Client | Debasish | 2016-04-15 | Closed/16-Apr-16
Gist of the Meeting
S.No. | Agenda Item |  |  | Highlights/ Observations/ Conclusions
1 | Progress Review of Web Application |  |  | Not Available
2 | Review of Mobile App UI Design |  |  | Not Available
Action Points
S.No. | Action | Responsibility | Projected Date of completion | Closure status/ Date of closure | Remarks
1 | Web Application need to be Closed | Debasish | 2016-04-28
2 | Mobile App UI Design need to be approved from Client | Debasish | 2016-04-25
Recorded By |  | Luminous Infoways Pvt. Ltd.