## MoM
Minutes of Meeting
Project Name /Function Name |  | OMMCOM NEWS |  | Date | 2016-05-13
Meeting Called By |  | Tanmay Mohanty |  | Topic | Review of Progess of Development
Schedule Time of Start |  | Actual Time of Start |  | Venue
05.00 PM |  | 05.00 PM |  | Luminous Infoways Pvt. Ltd, BBSR
Planned Duration of the Meeting |  | Actual Duration of the Meeting |  | Date/ Time/ Venue of Next Meeting
1 Hours |  | 1:00 Hrs |  | 27-May-2016/5:00 PM/Luminous Infoways Pvt. Ltd.
Members Present |  | Satyakam Misra (System Analyst), Debasish Mishra (PM), Mr. Tanmay Mohanty(CEO), Sarada Prasana Behera(DGM Op.), Mausumi Panda(QA), Samadhan Mishra(Technical Architect)
Members Absent |  | Not Available
Invitees |  | Not Available
Objectives of the Meeting |  | Discussion on Progress of the OMMCOM Application
Pending Action Points from Previous Meeting
S.No. | Action/ Observation | Responsibility | Projected Date of completion | Closure status/ Date of closure | Remarks
1 | Hosting of Web Application in Server | Debasish | 2016-05-10 | Closed/10-May-16
2 | Mobile App Development need to be closed other than video conference | Debasish | 2016-05-12 | Closed/12-May-16
3 | Review of Test Plan | Mausumi | 2016-05-10 | Closed/10-May-16
Gist of the Meeting
S.No. | Agenda Item |  |  | Highlights/ Observations/ Conclusions
1 | Review of Mobile App |  |  | Not Available
2 | Review of Video Conferencing in Mobile App |  |  | Not Available
3 | Review of Test Cases |  |  | Not Available
Action Points
S.No. | Action | Responsibility | Projected Date of completion | Closure status/ Date of closure | Remarks
1 | Development of Mobile App to be closed | Debasish | 2016-05-25
2 | Video Conferencing need to be Stable in Mobile App | Debasish | 2016-05-26
3 | Test Cases needs to be submitted to client | Mausumi | 2016-05-14
Recorded By |  | Luminous Infoways Pvt. Ltd.