## Version History
Metrics Analysis Report - Development Projects v 1.0
Sl. No. | Version No | Date | Prepared by | Reviewed by | Reviewed On | Approved by | Approved on | Change Details
1 | 1 | 2016-04-05 | Debasish Mishra | Sarada Prasana Behera | 2016-04-06 | Sarada Prasana Behera | 2016-04-06 | Initial Release
Classification: Luminous Infoways Pvt. Ltd ¦ CONFIDENTIAL/INTERNAL/PUBLIC

## Project Profile
Metrics Analysis Report - Development Projects v 1.0
Project Name | OMMCOM NEWS
Project Code | LIPL/PR/SD/0246
Team Lead | Subrat Rout
Project Manager | Debasish Mishra
Project Start Date | 2016-04-01
Project tentative end date | 2016-05-30

## Schedule Metrics
Metrics Analysis Report - Development Projects v 1.0
SCHEDULE VARIANCE
Ver. or Release No. / Phases | Planned Start Date | Revised Planned Start Date | Planned End Date | Revised Planned End Date | Actual Start Date | Actual End Date | Planned Duration (Person Days) | Planned Duration (against revised estimate) (Person days) | Actual Duration (Person Days) | % Variance (against planned) | % Variance (against revised estimate)
Iteration-1
Requirements | 2016-04-05 | 2016-04-05 | 2016-04-07 | 2016-04-07 | 2016-04-05 | 2016-04-07 | 3 | 3 | 3 | 0% | 0%
Requirements Review | 2016-04-08 | 2016-04-08 | 2016-04-08 | 2016-04-08 | 2016-04-08 | 2016-04-08 | 1 | 1 | 1 | 0% | 0%
Requirements Rework | 2016-04-09 | 2016-04-09 | 2016-04-12 | 2016-04-12 | 2016-04-09 | 2016-04-12 | 4 | 4 | 4 | 0% | 0%
Design | 2016-04-14 | 2016-04-13 | 2016-04-15 | 2016-04-14 | 2016-04-13 | 2016-04-14 | 2 | 1 | 2 | 0% | 100%
Design Review | 2016-04-15 | 2016-04-14 | 2016-04-15 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 1 | 1 | 1 | 0% | 0%
Design Rework | 2016-04-15 | 2016-04-15 | 2016-04-16 | 2016-04-15 | 2016-04-15 | 2016-04-15 | 2 | 1 | 1 | -50% | 0%
Coding | 2016-04-18 | 2016-04-18 | 2016-05-18 | 2016-05-19 | 2016-04-18 | 2016-05-19 | 31 | 32 | 32 | 3.226% | 0%
Code Review | 2016-05-19 | 2016-05-20 | 2016-05-21 | 2016-05-21 | 2016-05-19 | 2016-05-21 | 3 | 5 | 3 | 0% | -40%
Code Rework | 2016-05-21 | 2016-05-23 | 2016-05-23 | 2016-05-23 | 2016-05-23 | 2016-05-23 | 3 | 1 | 1 | -66.67% | 0%
Unit Testing | [6 empty] | 1 | 1 | 1 | 0% | 0%
Unit test case Review | [6 empty] | 1 | 1 | 1 | 0% | 0%
Test case Design | 2016-05-11 | 2016-05-11 | 2016-05-14 | 2016-05-14 | 2016-05-11 | 2016-05-14 | 4 | 1 | 4 | 0% | 300%
Test case Review | 2016-05-14 | 2016-05-14 | 2016-05-18 | 2016-05-18 | 2016-05-14 | 2016-05-18 | 5 | 5 | 5 | 0% | 0%
Test case Rework | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 1 | 1 | 1 | 0% | 0%
Testing | 2016-05-14 | 2016-05-14 | 2016-05-23 | 2016-05-25 | 2016-05-14 | 2016-05-25 | 10 | 12 | 12 | 20% | 0%
Acceptance | 2016-05-26 | 2016-05-26 | 2016-05-28 | 2016-05-28 | 2016-05-27 | 2016-05-28 | 3 | 1 | 2 | -33.33% | 100%
Support | [6 empty] | 1 | 1 | 1 | 0% | 0%
Schedule Variance for Iteration-1 | 2016-04-05 | 2016-04-05 | 2016-05-28 | 2016-05-28 | 2016-04-05 | 2016-05-28 | 54 | 54 | 54 | -126.8% | 460%
Iteration-2
Requirements | [6 empty] | 0 | 0 | 0
Requirements Review | [6 empty] | 0 | 0 | 0
Requirements Rework | [6 empty] | 0 | 0 | 0
Design | [6 empty] | 0 | 0 | 0
Design Review | [6 empty] | 0 | 0 | 0
Design Rework | [6 empty] | 0 | 0 | 0
Coding | [6 empty] | 0 | 0 | 0
Code Review | [6 empty] | 0 | 0 | 0
Code Rework | [6 empty] | 0 | 0 | 0
Unit Testing | [6 empty] | 0 | 0 | 0
Unit test case Review | [6 empty] | 0 | 0 | 0
Test case Design | [6 empty] | 0 | 0 | 0
Test case Review | [6 empty] | 0 | 0 | 0
Test case Rework | [6 empty] | 0 | 0 | 0
Testing | [6 empty] | 0 | 0 | 0
Acceptance | [6 empty] | 0 | 0 | 0
Support | [6 empty] | 0 | 0 | 0
Schedule Variance for Iteration-2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
Total Schedule Variance for the Project | 0 | 0 | 2016-05-28 | 2016-05-28 | 0 | 0 | 54 | 54 | 54 | -126.8% | 460%
Formulas:
Planned Start Date = IF(SUM(B8:[Planned Start Date, row above])="","",MIN(B8:[Planned Start Date, row above]))
Planned Start Date = IF( SUM(B25,[Planned Start Date, row above],)="","",MIN(B25,[Planned Start Date, row above]))
Revised Planned Start Date = IF(SUM(C8:[Revised Planned Start Date, row above])="","",MIN(C8:[Revised Planned Start Date, row above]))
Revised Planned Start Date = IF( SUM(C25,[Revised Planned Start Date, row above],)="","",MIN(C25,[Revised Planned Start Date, row above]))
Planned End Date = IF(SUM(D8:[Planned End Date, row above])="","",MAX(D8:[Planned End Date, row above]))
Planned End Date = IF(SUM(D25,[Planned End Date, row above])="","",MAX(D25,[Planned End Date, row above]))
Revised Planned End Date = IF(SUM(E8:[Revised Planned End Date, row above])="","",MAX(E8:[Revised Planned End Date, row above]))
Revised Planned End Date = IF(SUM(E25,[Revised Planned End Date, row above])="","",MAX(E25,[Revised Planned End Date, row above]))
Actual Start Date = IF(SUM(F8:[Actual Start Date, row above])="","",MIN(F8:[Actual Start Date, row above]))
Actual Start Date = IF( SUM(F25,[Actual Start Date, row above])="","",MIN(F25,[Actual Start Date, row above]))
Actual End Date = IF(SUM(G8:[Actual End Date, row above])="","",MAX(G8:[Actual End Date, row above]))
Actual End Date = IF( SUM(G25,[Actual End Date, row above])="","",MIN(G25,[Actual End Date, row above]))
Note on B6: Format : dd-mmm-yyyy

## Effort Metrics
Metrics Analysis Report - Development Projects v 1.0
EFFORT VARIANCE
Ver. or Release No. / Phases | Planned Effort (Person days) | Revised Planned Effort (Person Days) | Actual Effort (Person Days) | %variance against planned | %Variance against Revised planned
Iteration-1
Requirements | 3 | 3 | 3 | 0% | 0%
Requirements Review | 1 | 1 | 1 | 0% | 0%
Requirements Rework | 4 | 4 | 4 | 0% | 0%
Design | 2 | 2 | 2 | 0% | 0%
Design Review | 1 | 1 | 1 | 0% | 0%
Design Rework | 1 | 1 | 1 | 0% | 0%
Coding | 28 | 28 | 28 | 0% | 0%
Code Review | 3 | 3 | 3 | 0% | 0%
Code Rework | 1 | 1 | 1 | 0% | 0%
Unit Testing
Unit test case Review
Test case Design | 4 | 4 | 4 | 0% | 0%
Test case Review | 3 | 3 | 3 | 0% | 0%
Test case Rework | 1 | 1 | 1 | 0% | 0%
Testing | 10 | 10 | 10 | 0% | 0%
Acceptance | 2 | 2 | 2 | 0% | 0%
Support
Project Management
PPQA (Audits)
Risk Mgmt
Config Mgmt
Others (DAR, Analysis & Resolution, Misc)
Effort Variance for Iteration No: <1> | 64 | 64 | 64
Iteration No. <<2>>
Requirements
Requirements Review
Requirements Rework
Design
Design Review
Design Rework
Coding
Code Review
Code Rework
Unit Testing
Unit test case Review
Test case Design
Test case Review
Test case Rework
Testing
Acceptance
Support
Project Management
PPQA (Audits)
Risk Mgmt
Config Mgmt
Others (DAR, Analysis & Resolution, Misc)
Effort Variance for Iteration No: <2>
Total Effort Variance for the Project | 64 | 64 | 64

## Defects Metrics
Metrics Analysis Report - Development Projects v 1.0
Review Effectiveness
| No. of Reviews Iteration No. <<1>> | No. of Reviews Iteration No. <<2>>
Requirements | 0
Design | 0
Coding | 2
Testing | 33
Documentation | 0
Support | 0
Others (DAR, Analysis & Resolution, Misc) | 0
Total number of Defects | 35 | 0
SIZE VARIANCE
Version / Release No. | Estimated Size (size units) | Actual Size (size units)
Beta Version | 25 | 22
Final Release | 12 | 12
DEFECT DENSITY
Phase/Iteration | No. of Defects Iteration No. <<1>> | No. of Defects Iteration No. <<2>>
Requirements | 0 | 0
Design | 0 | 0
Coding | 2 | 0
Testing | 33 | 0
Note on B6: Review Defects
Note on C6: Review Defects
Note on B17: Estimated effort / Total no.of requirements
Note on C17: Planned effort / Total no.of requirements
Note on B23: Reviews+Testing Defects
Note on C23: Reviews+Testing Defects

## ProjectData-GraphicalView (hidden)
PROJECT METRICS - GRAPHICAL VIEW
Within Iteration - Against Planned
Iterations | Requirements | Requirements Review | Requirements Rework | Design | Design Review | Design Rework | Coding | Code Review | Code Rework | Unit Testing | Unit test case Review | Test case Design | Test case Review | Test case Rework | Testing | Testing Rework | Acceptance | Project Management | PPQA (Audits) | Risk Mgmt | Config Mgmt | Others (DAR, Analysis & Resolution, Misc)
Iteration 1 | 0 | 0 | 0 | 0 | 0 | -0.5 | 0.032258 | 0 | -0.66667 | 0 | 0 | 0 | 0 | 0 | 0.2 | #REF! | -0.33333 | #REF! | #REF! | #REF! | #REF! | #REF!
Iteration 2 | [15 empty] | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
UCL | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
LCL | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Within Iteration - Against Revised Plan (Schedule)
Iterations | Requirements | Requirements Review | Requirements Rework | Design | Design Review | Design Rework | Coding | Code Review | Code Rework | Unit Testing | Unit test case Review | Test case Design | Test case Review | Test case Rework | Testing | Testing Rework | Acceptance | Project Management | PPQA (Audits) | Risk Mgmt | Config Mgmt | Others (DAR, Analysis & Resolution, Misc)
Iteration 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | -0.4 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | #REF! | 1 | #REF! | #REF! | #REF! | #REF! | #REF!
Iteration 2 | [15 empty] | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF!
UCL | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
LCL | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Within Iteration - Against Planned
Iterations | Requirements | Requirements Review | Requirements Rework | Design | Design Review | Design Rework | Coding | Code Review | Code Rework | Unit Testing | Unit test case Review | Test case Design | Test case Review | Test case Rework | Testing | Testing Rework | Acceptance | Project Management | PPQA (Audits) | Risk Mgmt | Config Mgmt | Others (DAR, Analysis & Resolution, Misc)
Iteration 1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Iteration 2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
UCL | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
LCL | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Within Iteration - Against Revised Planned(Effort)
Iterations | Requirements | Requirements Review | Requirements Rework | Design | Design Review | Design Rework | Coding | Code Review | Code Rework | Unit Testing | Unit test case Review | Test case Design | Test case Review | Test case Rework | Testing | Testing Rework | Acceptance | Project Management | PPQA (Audits) | Risk Mgmt | Config Mgmt | Others (DAR, Analysis & Resolution, Misc)
Iteration 1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Iteration 2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
UCL | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
LCL | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Defect Metrics
Phase | Iteration No. <<1>> | Iteration No. <<2>> | Iteration No. <<3>> | Total No of Defects
Requirements | 0 | 0 | #REF! | 0
Design | 0 | 0 | #REF! | 0
Coding | 2 | 0 | #REF! | 0
Testing | 33 | 0 | #REF! | 0
Documentation | 0 | 0 | #REF! | 0
Others (DAR, Analysis & Resolution, Misc) | 0 | 0 | #REF! | 0
Total number of Defects | 35 | 0 | #REF! | 0