## Version History
Issue Tracker v 1.0
Sl. No. | Version No | Date | Prepared by | Reviewed by | Reviewed On | Approved by | Approved on | Change Details
1 | 1 | 2016-04-25 | Debasish Mishra | Sarada Prasana Behera | 2016-04-25 | Sarada Prasana Behera | 2016-04-25 | Initial Release
Classification: Luminous Infoways Pvt. Ltd. ¦ CONFIDENTIAL/INTERNAL/PUBLIC

## Technical Issues
Technical Issue Tracker
Issue no | Details | Opened date | Category (High/Medium/Low) | Raised By | Responsibility | Resolution details | Projected Closed date | Closed date | Status | Remarks
Omc-2 | Click on the logo of OMMCOM News -->Link is Missing | 14-05-2016 | Medium | QA | Subrata | Link is provided | 30-05-2016
Omc-3 | Go to landing page of Weather Widget-->Weather widget should show the current weather of the location detected where the application is being browsed. Weather widget is not shown weather of the location detected where the application is being browsed. | 14-05-2016 | High | QA | Subrata | Weather widget is shown weather of the location detected where the application is being browsed. | 30-05-2016
Omc-4 | Click on the Google Map-->In google Map current address should shown-->Current address is not shown in google map. | 14-05-2016 | High | QA | Subrata | Current address is shown in google map. | 30-05-2016
Omc-5 | Click on Conferences-->Conferences page should show all the upcoming conferences--> Upcoming conferences are not showing By click on the link getting error message as “ Error Exception in ca50f94474642b88c2c56c9f46fa75e0 line 10:” | 14-05-2016 | High | QA | Subrata | All the Upcoming conferences are shown | 30-05-2016
Omc-6 | Click on any menu-->After visiting a same page multiple times, the viewer should asked to save the respective page as preference. After visiting a same page multiple times, the viewer is not asked to save the respective page as preference. | 14-05-2016 | High | QA | Subrata | After visiting a same page multiple times, the viewer is asked to save the respective page as preference. | 30-05-2016
Omc-7 | Click on Master-->Manage Role--> Manage Role Menu Should be Present in the list of main menu Manage role function is not available in the Master Menu | 14-05-2016 | High | QA | Subrata | Manage Role Menu is Present in the list of main menu | 30-05-2016
Omc-8 | Add role Page--> Select user type and Click on show--> Admin should get all the lists to Set role for the user type Page is getting refreshed Show Button Is not working | 14-05-2016 | High | QA | Subrata | Admin is getting all the lists to Set role for the user type | 30-05-2016
Onc-9 | Add role Page--> Click on user type--> It should open a drop down option and it should be sorted in alphabetical order Drop down option is opened Details are not sorted in alphabetical order | 14-05-2016 | High | QA | Subrata | Details are sorted in alphabetical order | 30-05-2016
Omc-10 | Support Task Section -->Click on Support task User should redirected respective Links / page Link is Missing | 14-05-2016 | High | QA | Subrata | Link is provided | 30-05-2016
Omc-11 | Click on Add user button on the Manage Users page Add user form should be opened with the below details :Full Name Email User Type Mobile No Password Confirm Password Date of Birth AgeAddress1 Address2City Field to fill up the details The above options are missing | 16-05-2016 | High | QA | Subrata | All the details are provided in Add user form | 30-05-2016
Omc-12 | Provide all the required details-->Select user type as Super admin --> enter mobile number --> Provide date of birth and fill all the fields--> Click on save A new user should be created New user is not created . Getting error message as "The contact no may not be greater than 10. And The age may not be greater than 3." | 16-05-2016 | High | QA | Subrata | After providing all the required details new user is created. | 30-05-2016
Omc-13 | Click on Manage User-->Manage User Type-->Edit User should get an message That Do You Want To Edit the User with Yes or No option Popup is not coming | 16-05-2016 | High | QA | Subrata | User is getting the Yes/No popup | 30-05-2016
Omc-14 | Click on Manage User--> Manage User Type-->Delete User should get an message That Do You Want To Delete the User with Yes or No option Popup is not coming | 16-05-2016 | High | QA | Subrata | User is getting the popup message | 30-05-2016
Omc-15 | Click on Manage User-->Manage User Type -->Deactivate option User should get an message That Do You Want To Deactivate the User with Yes or No option Popup is not coming | 16-05-2016 | High | QA | Subrata | User is getting the popup message | 30-05-2016
Omc-16 | Add User-->Provide all the required details-->Select user type as Super admin -->enter mobile number --> Provide date of birth and fill all the fields--> Click on save A new user should be created New user is not created .Getting error message as "The contact no may not be greater than 10.And The age may not be greater than 3." | 16-05-2016 | High | QA | Subrata | After providing all the required details new user is created. | 30-05-2016
Omc-17 | Click on News--> Manage News category--> Add News Category-->Fill all the details & Click on save--> It should save the details and redirect the admin to the news category list page Fatal Error Exception in Master Controller .php line 438: Call to a member function is Valid() on a non-object | 16-05-2016 | High | QA | Debasrita | After providing all the required details a new category is created | 30-05-2016
Omc-18 | Click on edit option --> edit the Details --> click on save--> User should redirected to the admin page after updated the details Fatal Error Exception in Master Controller .php line 426: Call to a member function is Valid() on a non-object | 16-05-2016 | High | QA | Debasrita | User is redirected to the User listing page | 30-05-2016
Omc-19 | Keep Blank-->News Title-->From Date-->To Date --> News Category-->Status Click on Search User should get an error message that fill respective Field Error messages are not showing | 16-05-2016 | Low | QA | Debasrita | DB connection rectified | 30-05-2016
Omc-20 | Click on Upload section-->User should get an message only (jpeg,jpg,png,gif) format file can upload Message are not coming | 16-05-2016 | Low | QA | Debasrita | Images uploaded | 30-05-2016
Omc-21 | Click on Delete Option--> It should Delete the Image But Image is Present in the database | 16-05-2016 | Midium | QA | Debasrita | Admin previleges flushed | 30-05-2016
Omc-22 | Click on Upload section --> User should get an message only ( .flv, .vob,mp4, .m4p, .m4v, .flv, . f4v , etc ) format file can upload User is not getting any message | 16-05-2016 | Midium | QA | Debasrita | User is getting message | 30-05-2016
Omc-23 | While Uploading Video-->Click on Add--> User should get an message that Please wait Video is uploading Message appeared Invalid request, please try again . Insteed of Please wait Video is uploading. Uploading Stopped Note: Uploading should not be stopped | 16-05-2016 | High | QA | Debasrita | User is getting message | 30-05-2016
Omc-24 | Click on Disable Option--> after adding the video In action panel It should Disable the Videos With a message Video was disable successful Disable Button Status should be Change to Enable Not Found Http Exception in Route Collection .php line 161: | 17-05-2016 | High | QA | Debasrita | Videos are getting disabled with the proper message | 30-05-2016
Omc-25 | Click on Delete option--> After adding the video in action panel Video should be deleted While click on delete getting error message as “NotFoundHttpException in RouteCollection.php line 161:” | 17-05-2016 | High | QA | Debasrita | Videos are getting deleted | 30-05-2016
Omc-26 | Click on Sub News Category It should open all the lists of sub Category Sub category of news are not shown | 17-05-2016 | High | QA | Debasrita | News sub categories are shown | 30-05-2016
Omc-36 | Manage News-->Click on Reject If article needs changes, the admin or the respective authorized user should reject by clicking on “Reject” button. Reject form should contains: Remarks for Rejecting text area. Reject button Cancel button Reject button is missing | 17-05-2015 | High | QA | Debasrita | News are getting rejected by the admin or the respective authorized users | 30-05-2016
Omc-37 | Manage News-->Theme Admin should be able to add/manage theme for the News/Article add/manage theme details are missing. | 17-05-2014 | High | QA | Debasrita | Admin are addding/updating the News theme | 30-05-2016
Omc-38 | Manage Votes-->Add Poll “Add Poll” and Manage Polls/Votes menus should be available Instead of “Add Poll” and Manage Polls/Votes menus its showing Add Questions and Manage questions | 17-05-2013 | High | QA | Debasrita | “Add Poll” and Manage Polls/Votes menus are shown | 30-05-2016
Omc-39 | Click on Social Media links Viewers should be able to share the news, articles, videos, etc. in social media Links are missing | 20-05-2012 | High | QA | Debasrita | Viewers are sharing the news, articles, videos, etc. in social media | 30-05-2016
Omc-40 | Click on Audit Trail Report Viewers information should be captured when he/she comments or requests to join a video conference Audit trail report is missing | 20-05-2012 | High | QA | Debasrita | Viewers information are getting captured | 30-05-2016
Omc-41 | Admin & Authorized users should able to block any respective viewer's activity by click on the “Block” button Audit log report is missing | 21-05-2012 | High | QA | Debasrita | Admin & Authorized users are able to block any respective viewer's activity by click on the “Block” button | 30-05-2016
Omc-42 | Click on Audit log Report Admin and authorized users should view all the activities taking place in the application in the audit log report Audit log report is missing | 21-05-2012 | High | QA | Debasrita | Admin and authorized users are viewed all the activities taking place in the application in the audit log report | 30-05-2016
Omc-43 | Click on Audit log Report Admin and authorized users should view all the activities taking place in the application in the audit log report Audit log report is missing | 23-05-2012 | High | QA | Debasrita | Admin and authorized users are viewed all the activities taking place in the application in the audit log report | 30-05-2016

## NonTechnical Issues
Non Technical Issue Tracker
Issue no | Details | Opened date | Category(h/m/l) | Raised By | Impact | Responsibility | Projected Closure Date | Resolution details | Closed date | status | Remarks
1 | Invoice delayed | 2016-04-15 | h | OP Team |  | Jitesh Jena | 2016-04-20 | Communication made by Mr. Jitesh with Operation team | 2016-04-20 | Complete