## MoM
Minutes of Meeting
Project Name /Function Name |  | OMMCOM NEWS |  | Date | 2016-04-01
Meeting Called By |  | Tanmay Mohanty |  | Topic | Kick Off Meeting
Schedule Time of Start |  | Actual Time of Start |  | Venue
03.00 PM |  | 15:15 |  | Luminous Infoways Pvt. Ltd, BBSR
Planned Duration of the Meeting |  | Actual Duration of the Meeting |  | Date/ Time/ Venue of Next Meeting
2 Hours |  | 2:00 Hrs |  | 7-Apr-2016/5:00 PM/Luminous Infoways Pvt. Ltd.
Members Present |  | Satyakam Misra (System Analyst), Debasish Mishra (PM), Mr. Tanmay Mohanty(CEO), Sarada Prasana Behera(DGM Op.), Mausumi Panda(QA), Prativa Rani Samal(HR), Samadhan Mishra(System Architect)
Members Absent |  | Nil
Invitees |  | Not Available
Objectives of the Meeting |  | Discussion on Development of the Application
Pending Action Points from Previous Meeting
S.No. | Action/ Observation | Responsibility | Projected Date of completion | Closure status/ Date of closure | Remarks
Gist of the Meeting
S.No. | Agenda Item |  |  | Highlights/ Observations/ Conclusions
1 | Discussion on Scope of the Application |  |  | Not Available
2 | Resource Finalization |  |  | Not Available
3 | Discussion on Deliverables |  |  | Not Available
4 | Implementation of Feng Office |  |  | Not Available
Action Points
S.No. | Action | Responsibility | Projected Date of completion | Closure status/ Date of closure | Remarks
1 | Project Plan need to be submitted | Debasish | 2016-04-02
2 | Finalization of Resources | Debasish | 2016-04-02
3 | Allocation of Task to resources | Debasish | 2016-04-02
4 | Implementation of Feng Office | Debasish | 2016-04-04
Recorded By |  | Luminous Infoways Pvt. Ltd.