## MoM
Minutes of Meeting
Project Name /Function Name |  | OMMCOM NEWS |  | Date | 2016-04-07
Meeting Called By |  | Tanmay Mohanty |  | Topic | Review of Progess of Development
Schedule Time of Start |  | Actual Time of Start |  | Venue
05.00 PM |  | 05.00 PM |  | Luminous Infoways Pvt. Ltd, BBSR
Planned Duration of the Meeting |  | Actual Duration of the Meeting |  | Date/ Time/ Venue of Next Meeting
1 Hours |  | 1:00 Hrs |  | 16-Apr-2016/5:00 PM/Luminous Infoways Pvt. Ltd.
Members Present |  | Satyakam Misra (System Analyst), Debasish Mishra (PM), Mr. Tanmay Mohanty(CEO), Sarada Prasana Behera(DGM Op.), Mausumi Panda(QA), Samadhan Mishra(Technical Architect)
Members Absent |  | Not Available
Invitees |  | Not Available
Objectives of the Meeting |  | Discussion on Progress of the OMMCOM Application
Pending Action Points from Previous Meeting
S.No. | Action/ Observation | Responsibility | Projected Date of completion | Closure status/ Date of closure | Remarks
1 | Project Plan need to be submitted | Debasish | 2016-04-02 | Closed/2-Apr-16
2 | Finalization of Resources | Debasish | 2016-04-02 | Closed/2-Apr-16
3 | Allocation of Task to resources | Debasish | 2016-04-02 | Closed/2-Apr-16
4 | Implementation of Feng Office | Debasish | 2016-04-04 | Closed/4-Apr-16
Gist of the Meeting
S.No. | Agenda Item |  |  | Highlights/ Observations/ Conclusions
1 | Review on 1st Draft SRS |  |  | Not Available
2 | Review on Technical Solution of Application |  |  | Not Available
3 | Review on UI Design |  |  | Not Available
Action Points
S.No. | Action | Responsibility | Projected Date of completion | Closure status/ Date of closure | Remarks
1 | SRS need to be Complete in all aspect | Satyakam | 2016-04-13
2 | Technical Solution of the Application need to be freezed | Samadhan | 2016-04-15
3 | UI needs to be approved from the Client | Debasish | 2016-04-15
Recorded By |  | Luminous Infoways Pvt. Ltd.