## MoM
Minutes of Meeting
Project Name /Function Name |  | OMMCOM NEWS |  | Date | 2016-05-28
Meeting Called By |  | OMMCOM |  | Topic | Application Demonstration
Schedule Time of Start |  | Actual Time of Start |  | Venue
05.00 PM |  | 05.30 PM |  | OMMCOM OFFICE, BOMIKHAL, BHUBANESWAR
Planned Duration of the Meeting |  | Actual Duration of the Meeting |  | Date/ Time/ Venue of Next Meeting
2 Hours |  | 3.00 Hrs
Members Present |  | Satyakam Misra (System Analyst), Debasish Mishra (PM), Mr. Jajati Karan (OMMCOM)
Members Absent
Invitees
Objectives of the Meeting |  | Functional demonstration of the website and Mobile Application
Pending Action Points from Previous Meeting
S.No. | Action/ Observation | Responsibility | Projected Date of completion | Closure status/ Date of closure | Remarks
1 | Hosting of Web Application on Server | Debasish | 2016-05-05 | Closed/5-May-16
Gist of the Meeting
S.No. | Agenda Item |  |  | Highlights/ Observations/ Conclusions
1 | Demo of Mobile Application with Video Conferencing
Action Points
S.No. | Action | Responsibility | Projected Date of completion | Closure status/ Date of closure | Remarks
1 | Hosting of Mobile Application & Video Conferencing on Server | Debasish | 2016-05-30
Recorded By |  | Luminous Infoways Pvt. Ltd.