## Version History
Status Reports for Functions v 1.0
Sl. No. | Version No | Date | Prepared by | Reviewed by | Reviewed On | Approved by | Approved on | Change Details
1 | 1 | 2016-05-15 | Debasish Mishra | Sarada Prasana Behera | 2016-05-17 | Sarada Prasana Behera | 2016-05-17
Classification: Luminous infoways Pvt. Ltd. ¦ CONFIDENTIAL/INTERNAL/PUBLIC

## Report
Status Reports for Functions v 1.0
Function Name | User Manual Preparation |  |  | Reported By | Mausumi Panda
Reporting Period From | 2016-04-01 |  |  | Date of Reporting
To | 2016-05-28
Quality Objectives :
Item | Target Set | Achievement | Remarks
1 | Understanding | Done
2 | Business Abstract | Done
3 | Modules Categorisation | Done
4 | Review from Manager | Done
5 | Review from Client
Achievements/ Milestones
Status of the Planned Tasks for the Reporting Period
S.No | Tasks | Description of Tasks |  | Status |  | Remarks
|  |  |  | Completed | In Process
1 | Gather initial requirement | Communicate with client and System analyst to gather primary objective of the application |  | Yes
2 | Prepare screenshots and writeups | Understand the business & application logic |  | Yes
3 | Syummarize the sequence of operations, user interactions | User interactions and each operation symbolized by sequence diagrams, to be complied in the user manual |  |  | Yes
Major Activities Planned for the Next Month :
S.No. | Tasks | Description of Tasks |  | Target Date
1 | Record impact of last stable release | Record step-by-step impact of last stable release, in bullets represent infront of technical team |  | 2016-06-01
2 | Record possibilities in new functionalities | Newly added functionalities may need to be revamped, need to freeze the discussions |  | 2016-06-05
3 | Record user's interaction and skill improvement | Another level training to be scheduled to demonstrate newly added functionalities |  | 2016-06-07
Suggestions for Improvement: | Add more graphics to user manuals, make the index page of the manual more appealing
Open Issues/ Areas of oncerns: | Summary section of the document, modular division of functionalities to be properly mentioned
Note on G21: Specify Revised Target if not completed