## Version History
Requirements Log v 1.1
Project: OMMCOM News
Sl. No. | Version No. | Date | Prepared By | Reviewed By | Reviewed On | Approved By | Approved On | Change Details
1 | V 1.0 | 2016-04-05 | Satyakam Misra | Debasish Mishra | 2016-04-05 | Debasish Mishra | 2016-04-05 | First Release
2 | V 1.1 | 2016-04-12 | Satyakam Misra | Debasish Mishra | 2016-04-12 | Debasish Mishra | 2016-04-12 | Social Share, News Details screen & Breaking News functionality updated. Date Due, Assigned To added, Status against each requirement updated
Classification:Luminous Infoways Pvt. Ltd. ¦ CONFIDENTIAL

## Requirements Log
Requirements Log
| Updated By | Updated On
| Satyakam Misra | 12th April 2016
|  | REQUIREMENT |  |  | PRIORITY |  | STATUS |  |  |  |  | NOTES
Sl No | ID | Req Type | Category | Requirement | Imp Weight (1 - 5) | Priority | Status | Date Created | Date Due | Assigned to | Requested By
1 | OMMCOM-Req 01 | User Interface | Landing Page (Web) | All viewers shall be able to view the landing page of the web application. | 5 | High | Approved | 2016-04-05 | 2016-04-19 | Debi Prasad Behra | Mr. Jajati Karan (OMMCOM Media)
2 | OMMCOM-Req 02 / OMMCOM-CR-2 | Functional | Landing Page :: Breaking News (Web) | All viewers shall be able to see the breaking news section. Breaking News label shall be shown after every 3 breaking news shows up. | 4 | High | Approved | 2016-04-12 | 2016-04-21 | Subrata Rout | Mr. Jajati Karan (OMMCOM Media)
3 | OMMCOM-Req 03 | Functional | News Details Page (Web) | All the viewers shall be able to read the detailed news under News Details page | 4 | High | Approved | 2016-04-05 | 2016-04-21 | Subrata Rout | Mr. Jajati Karan (OMMCOM Media)
4 | OMMCOM-Req 04 | User Interface | Landing Screen (Mobile) | All viewers shall be able to view the landing screen of the mobile app. | 5 | High | Approved | 2016-04-05 | 2016-04-19 | Suhasini Reddy | Mr. Jajati Karan (OMMCOM Media)
5 | OMMCOM-Req 05 / OMMCOM-CR-2 | Functional | Landing Screen (Mobile) | All viewers shall be able to see the breaking news section. Breaking News label shall be shown after every 3 breaking news shows up. | 4 | High | Approved | 2016-04-12 | 2016-04-23 | Suhasini Reddy | Mr. Jajati Karan (OMMCOM Media)
6 | OMMCOM-Req 06 / OMMCOM-CR-1 | Functional | News Details Screen (Mobile) | All the viewers shall be able to read the detailed news under News Details screen. News details screen shall have flip effect to see the entire News details. | 4 | High | Approved | 2016-04-12 | 2016-04-23 | Suhasini Reddy | Mr. Jajati Karan (OMMCOM Media)
7 | OMMCOM-Req 07 | User Interface | Landing Page (Web) Landing Screen (Mobile) | Viewer shall be asked to save his/her preference if frequently visits a single section. | 3 | Med | Approved | 2016-04-05 | 2016-04-25 | Subrata Rout, Suhasini Reddy | Mr. Jajati Karan (OMMCOM Media)
8 | OMMCOM-Req 08 | Functional | Role Management (Web) | Admin shall be able to create/manage roles using the role management feature. | 4 | Med | Approved | 2016-04-05 | 2016-04-26 | Debasrita Mohanty | Mr. Jajati Karan (OMMCOM Media)
9 | OMMCOM-Req 09 | Functional | User Management (Web) | Admin shall be able to add/manage users using the user management feature. | 4 | Med | Approved | 2016-04-05 | 2016-04-26 | Debasrita Mohanty | Mr. Jajati Karan (OMMCOM Media)
10 | OMMCOM-Req 10 | Functional | Content Management System (CMS) (Web) | Admin shall be able to add/manage news categories. | 4 | High | Approved | 2016-04-05 | 2016-04-26 | Debasrita Mohanty | Mr. Jajati Karan (OMMCOM Media)
11 | OMMCOM-Req 11 | Functional | Content Management System (CMS) (Web) | Content Writers & Admin shall be able to write news for respective news categories. | 5 | High | Approved | 2016-04-05 | 2016-04-29 | Debasrita Mohanty | Mr. Jajati Karan (OMMCOM Media)
12 | OMMCOM-Req 12 | Functional | Content Management System (CMS) (Web) | Admin & the authorized user shall be able to moderate/approve the contents being published by the content writer | 4 | Med | Approved | 2016-04-05 | 2016-04-30 | Debasrita Mohanty | Mr. Jajati Karan (OMMCOM Media)
13 | OMMCOM-Req 13 | Functional | Content Management System (CMS) (Web) | After rejection, the respective content writer is allowed to edit the respective previously submitted news | 4 | Med | Approved | 2016-04-05 | 2016-04-30 | Debasrita Mohanty | Mr. Jajati Karan (OMMCOM Media)
14 | OMMCOM-Req 14 | Functional | Content Management System (CMS) (Web) | Admin shall be able to add/manage theme for the News publishing | 2 | Low | Approved | 2016-04-05 | 2016-05-03 | Debasrita Mohanty | Mr. Jajati Karan (OMMCOM Media)
15 | OMMCOM-Req 15 | Functional | Content Management System (CMS) (Web) | Admin shall be able to create Vote/Poll to which viewers can interact with | 3 | Med | Approved | 2016-04-05 | 2016-05-05 | Debasrita Mohanty | Mr. Jajati Karan (OMMCOM Media)
16 | OMMCOM-Req 16 | User Interface | Content Management System (CMS) (Web) | Viewers can participate in opinion polls | 4 | High | Approved | 2016-04-05 | 2016-04-28 | Subrata Rout, Suhasini Reddy | Mr. Jajati Karan (OMMCOM Media)
17 | OMMCOM-Req 17 | Functional | Video Conference (Web) | Admin and authorized users shall be able to create/manage Video Conference | 5 | High | Approved | 2016-04-05 | 2016-05-06 | Subrata Rout, Suhasini Reddy | Mr. Jajati Karan (OMMCOM Media)
18 | OMMCOM-Req 18 | User Interface | Video Conference (Web & Mobile) | View on-going Video Conference | 5 | High | Approved | 2016-04-05 | 2016-05-09 | Subrata Rout, Suhasini Reddy | Mr. Jajati Karan (OMMCOM Media)
19 | OMMCOM-Req 19 | Functional | Video Conference (Web: for moderator & viewer Mobile for viewer only) | Moderator shall be able to moderate the Video Conference processes | 4 | High | Approved | 2016-04-05 | 2016-05-12 | Subrata Rout | Mr. Jajati Karan (OMMCOM Media)
20 | OMMCOM-Req 20 / OMMCOM-CR-3 | Functional | Social Media (Web & Mobile) | Viewers shall be able to share any news/videos in social media. News shared in WhatsApp shall show the thumbnail of the respective news being shared. | 4 | High | Approved | 2016-04-12 | 2016-05-14 | Subrata Rout, Suhasini Reddy | Mr. Jajati Karan (OMMCOM Media)
21 | OMMCOM-Req 21 | Functional | Social Media (Web & Mobile) | Viewers shall be able to view What's trending in Social Media | 3 | Med | Approved | 2016-04-05 | 2016-05-14 | Subrata Rout, Suhasini Reddy | Mr. Jajati Karan (OMMCOM Media)
22 | OMMCOM-Req 22 | Communications | Audit Trail (Web) | Viewers shall be able to comment/edit their existing comments on any news, videos, etc. | 4 | Med | Approved | 2016-04-05 | 2016-05-17 | Subrata Rout, Suhasini Reddy | Mr. Jajati Karan (OMMCOM Media)
23 | OMMCOM-Req 23 | Communications | Audit Trail (Web) | Viewers information are captured when he/she comments or requests to join a video conference | 4 | Med | Approved | 2016-04-05 | 2016-05-12 | Subrata Rout, Suhasini Reddy | Mr. Jajati Karan (OMMCOM Media)
24 | OMMCOM-Req 24 | Security | Audit Trail (Web) | Admin & Authorized users shall able to block any respective viewer's activity | 4 | Med | Approved | 2016-04-05 | 2016-05-19 | Debasrita Mohanty | Mr. Jajati Karan (OMMCOM Media)
25 | OMMCOM-Req 25 | Audit | Audit Trail (Web) | Admin and authorized users shall be able to view all the activities taking place in the application in the audit log | 3 | Med | Approved | 2016-04-05 | 2016-05-20 | Subrata Rout | Mr. Jajati Karan (OMMCOM Media)
Note on D11: Select a Req type from the list.
Note on E11: e.g., Functional Area, Subject Area, Process, Activity, Use-Case, Event, Entity, Object, Component, etc.
Note on G11: From House of Quality Prioritization Analysis.
Note on H11: Select a priority from the list.
Note on I11: Select a status from the list.

## List Fields
Functional
Data | Status Fields | Priority Fields
Reporting / BI
System Interface | Proposed | High
User Interface | Approved | Med
Hardware | Specified | Low
Communications | WIP
Validation | Constructed
Performance | Verified
Reliability | Deployed
Availability | Active
Security | Deleted
Maintainability | Modified
Compliance | Deferred
Audit
Other
Operations
Training
Site