## Version History
Review Defect Log v 1.0
Sl. No. | Version No | Date | Prepared by | Reviewed by | Reviewed On | Approved by | Approved on | Change Details
1 | V1.0 | 10-05-2016 | Mausumi | Debasish Mishra | 10-05-2016 | Debasish Mishra | 10-05-2016 | First Release

## Review Details
Review Defect Log
| Project ID: | Ommcom
| Project Name: | Ommcom Media
| Customer: | OMMCOM Media Pvt. Ltd
Sl.No | Date of Review | Work Product Name | Version No. | Review Cycle | Size of the Work Product | Unit | Preparation Effort (In Person Hours) | Review Meeting Effort (In Person Hours) | Review Type | Reviewer(s) | Owner of the work Product | Review Result
1 | 10-05-2016 | Test Plan | V1.0 | 1 | 20 | Pages | 8 | 4 | One Person Review | Debasish Mishra | Ommcom Media | Pass
2 | 17-05-2016 | Test Cases | V1.0 | 1 |  | Function Point | 24 | 4 | One Person Review | Debasish Mishra | Ommcom Media | Pass

## Defects Details
Review Defect Log
Sl.No | Work Product Name | Version No. | Phase Detected | Defect Description | Severity | Priority | Defect Type | Defect Cause | Defect Status | Fixed By | Fixed Date | Verified By | Verified Date | Action Taken/ Remarks
1 | Test Plan | V1.0 | Test Plan Review | All the features were not mentioned | Medium | Medium | Test plans - Testability | Human - Communication | Fixed | Mausumi | 10-05-2016 | Debasish Mishra | 10-05-2016 | Modified | Work Product Name | Work Product Name | Version No | Version No | Defect Cause | Defect Type | Defect type for Analysis | Severity | Priority | Status | Phase Detected | Defect Injection Phase
2 | Test Cases | V1.0 | Test Cases Review | Test cases are missing for the few functionalities | Medium | Medium | Test plans - Incomplete test case | Human - Communication | Fixed | Mausumi | 18-05-2016 | Debasish Mishra | 18-05-2016 | Modified | Test Plan | Test Plan | V1.0 | V1.0 | Configuration - Improper Version of Sources | CM Plan - Naming conventions | Naming conventions | High | Low | Open / Reported | Requirments Review | Requirements Development
[15 empty] | Test Cases | Test Cases | V1.0 | V1.0 | Environment - Improper SW Configuration | CM Plan - Not a defect |  | Medium | Medium | Rejected | PMP Review | High Level Design
[15 empty] | 0 |  | 0 |  | Environment - Improper HW Configuration | CM Plan - Storage structure | Storage structure | Low | High | Fixed | CMP review | Detailed design
[15 empty] | 0 |  | 0 |  | Environment - Improper Utilities | CM Plan - Version control | Version control | Suggestion |  | Closed | HLD review | Coding
[15 empty] | 0 |  | 0 |  | External - Conflicting stakeholders | Code - Consistency | Consistency |  |  |  | Detailed Design Review | Project Planning
[15 empty] | 0 |  | 0 |  | External - Delay in Resolution of Issues | Code - Interface | Interface |  |  |  | Code Review
[15 empty] | 0 |  | 0 |  | Human - Communication | Code - Logic | Logic |  |  |  | Test Plan Review
[15 empty] | 0 |  | 0 |  | Human - Error in Translation | Code - Memory management | Memory management
[15 empty] | 0 |  | 0 |  | Human - Errors in Elicitation | Code - Not a defect
[15 empty] | 0 |  | 0 |  | Human - Ignorance | Code - Performance | Performance
[15 empty] | 0 |  | 0 |  | Human - Lack of Application Knowledge | Code - Portability | Portability
[15 empty] | 0 |  | 0 |  | Human - Lack of Domain Knowledge | Code - Redundant code | Redundant code
[15 empty] | 0 |  | 0 |  | Human - Lack of Technical Knowledge | Code - Reusability | Reusability
[15 empty] | 0 |  | 0 |  | Human - Lack of Tool Application Knowledge | Code - Standards | Standards
[15 empty] | 0 |  | 0 |  | Human - Omission | Code - Traceability | Traceability
[15 empty] | 0 |  | 0 |  | Human - Tendency to Over Commit | Code - User interface | User interface
[15 empty] | 0 |  | 0 |  | Human - Typography | Design - Interface | Interface
[15 empty] | 0 |  | 0 |  | Planning - Improper Deviation | Design - Logic | Logic
[15 empty] | 0 |  | 0 |  | Planning - Improper Lifecycle Model | Design - Naming conventions | Naming conventions
[15 empty] | 0 |  | 0 |  | Planning - Improper Tailoring | Design - Not a defect
[15 empty] | 0 |  | 0 |  | Planning - Inadequate Time for Activity | Design - Standards | Standards
[15 empty] | 0 |  | 0 |  | Process aids - Inadequate BOKs | Design - Traceability | Traceability
[15 empty] | 0 |  | 0 |  | Process aids - Inadequate Checklists | Design - Unclear requirements | Lack of clarity
[15 empty] | 0 |  | 0 |  | Process aids - Inadequate Guidelines | Impact analysis - Incomplete | Lack of completion
[15 empty] | 0 |  | 0 |  | Process aids - Inadequate Methodologies | Impact analysis - Inconsistent | Inconsistency
[15 empty] | 0 |  | 0 |  | Process aids - Inadequate Standards | Impact analysis - Non traceable | Traceability
[15 empty] | 0 |  | 0 |  | Process aids - Inadequate Templates | Impact analysis - Non verifiable | Non verifiable
[15 empty] | 0 |  | 0 |  | Process aids - No Online Checklists | Impact analysis - Standards | Standards
[15 empty] | 0 |  | 0 |  | Process aids - Non-detailing in Templates | Impact analysis - Unclear | Lack of clarity
[15 empty] | 0 |  | 0 |  |  | PM Plan - Not a defect
[15 empty] | 0 |  | 0 |  |  | PM Plan - Planning | Planning
[15 empty] | 0 |  | 0 |  |  | PM Plan - Traceability | Traceability
[15 empty] | 0 |  | 0 |  |  | Req Spec - Incomplete | Incomplete input
[15 empty] | 0 |  | 0 |  |  | Req Spec - Inconsistent | Inconsistency
[15 empty] | 0 |  | 0 |  |  | Req Spec - Incorrect | Incorrect/Invalid input
[15 empty] | 0 |  | 0 |  |  | Req Spec - Non Traceable | Traceability
[15 empty] | 0 |  | 0 |  |  | Req Spec - Non verifiable | Non verifiable
[15 empty] | 0 |  | 0 |  |  | Req Spec - Not a defect
[15 empty] | 0 |  | 0 |  |  | Req Spec - Standards | Standards
[15 empty] | 0 |  | 0 |  |  | Req Spec - Unclear | Lack of clarity
[20 empty] | Test plans - Incomplete test case | Incomplete input
[20 empty] | Test Plans - Invalid test case | Incorrect/Invalid input
[20 empty] | Test plans - Logic | Logic
Test plans - Not a defect
[20 empty] | Test plans - Standards | Standards
[20 empty] | Test plans - Testability | Not testable
[20 empty] | Test plans - Testing standards | Standards
[20 empty] | Test plans - Traceability | Traceability